## Gantt
[PROJECT NAME] - Basic Gantt Chart Excel Template | [34 empty] | Project Manager : | [5 empty] | [Project Manager] | [8 empty] | [Company Name]
| Input column |  |  |  | Project start date: | [20 empty] | 2022-01-03 | [23 empty] | 1
Calculated column
[5 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[5 empty] | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07 | 2022-01-03 | 2022-01-04 | 2022-01-05 | 2022-01-06 | 2022-01-07
TASK ID | TASK | START DATE | DURATION | END DATE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
Data Collection and Preprocessing
| Identify different ways of scraping data | 2022-01-03 | 2 weeks | 1900-01-01
| Learn the necessary techniques to scrape data | 2022-01-10 | 1 week | 1900-01-01
| Gather all data sources | 2022-01-19 | 3 weeks | 1900-01-01
| Store and preprocess data | 2022-01-21 | 2 weeks | 1900-01-01
| Identify data quality issues (Exploratory Data Analysis) | 2022-01-30 | 2 weeks
Sentiment Analysis
| Experiment various analysis techniques |  | 2 weeks
| Refine the models |  | 2 weeks
Comparative Analysis
| Conduct a detailed comparative analysis | 2022-01-28 | 1 week | 1900-01-01
| Identify sentiment patterns |  | 1 week | 1900-01-01
| Extract valuable insights | 2022-02-04 | 1 week | 1900-01-01
| Documentation |  |  | 1900-01-01
| Compile research findings | 2022-02-10 | 2 weeks | 1900-01-01
| Create visualisations | 2022-01-07 | 2 weeks | 1900-01-01
| Write the report |  | 3 weeks
| Prepare presentation |  | 1 week
| Submission | 2022-01-26 | 1 day | 1900-01-01
| Task 12 | 2022-01-26 | 6 | 1900-01-01
| Task 13 | 2022-02-04 | 8 | 1900-01-01
| Task 14 | 2022-02-17 | 4 | 1900-01-01
| Task 15 | 2022-02-24 | 3 | 1900-01-01
| Task 16 | 2022-01-10 | 8 | 1900-01-01
| Task 17 | 2022-01-12 | 3 | 1900-01-01
| Task 18 | 2022-01-17 | 6 | 1900-01-01
| Task 19 | 2022-01-27 | 4 | 1900-01-01
| Task 20 | 2022-02-07 | 6 | 1900-01-01

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (M3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TASK ID (optional), TASK NAME, START DATE, and number of WORKDAYS.
| • | To change the range of dates displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Please do not change the dates in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 29), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more dates in the timeline:
|  |  | Step 1: | Copy one-week columns (e.g. AU-AY)
|  |  | Step 2: | Select the column after the last date (AZ), then right click and select Insert Copied Cells.
The calculation for END DATE
| • | Please do not enter the end dates manually since END DATE is a calculated column.
| • | If you enter a start date, by default, the end date is the same as the start date.
| • | Once you add the number of workdays, the end date is automatically updated. Weekends are not included in the calculation.